## Slide 1: UNC Library Technology initiative proposal, review, and approval process
Jenn Riley
Head, Carolina Digital Library and Archives
UNC-Chapel Hill Library

## Slide 2: A familiar story (broadly told)
Administration’s perspective: Lack of accountability; need to understand the impact of proposed initiatives on technical staff.
Front line librarians’ perspective: We’re moving too slowly; I can’t get the support I need to follow through on my ideas.
Technical staff’s perspective: We can’t take on any more.

## Slide 3
It is not enough to have a good idea.
Notes: Our Library Technology Council was struggling allocating technology resources. Good proposals, unclear implementation plans, no way to balance them against one another.
Need culture of cultivating ideas, get many involved in planning/implementing. Leadership, wide perspective on the part of the proposer, engagement from technical staff, all willing to negotiate, compromise, and see the larger picture.
We don’t have this yet at UNC. So how do we get there?
Lots of discussion. Clear direction, priorities.
But we also attempted in one way to force the issue.

## Slide 4: Need a process that will
Encourage planning and ownership
Allow initiatives under consideration to be compared to one another
Provide a (not too burdensome) path for ideas to reach fruition
Ensure we can commit the resources necessary to succeed with those initiatives we do prioritize
Deal with all types of library technology initiatives

## Slide 5
Receive proposal
Assign CDLA facilitator
Post proposal for CDLA/Systems/LTC review
Report to LTC
Develop full project proposal/timeline
Develop basic project plan/timeline
Project/workflow/time analysis
General estimate of required resources
Identify stakeholders
Preliminary decision on proposal disposition
Candidate for fast-track approval
Require full LTC review
Approve and proceed immediately
Report to LTC
LTC semiannual review
Compare required resources to available resources
Place in holding queue for priority if resource availability changes
Resources become available before next LTC review
Final decision on proposal disposition
Resources available
Resources not available
No
Yes
Require full LTC review
Fast-track approval
Estimate of required resources
Absorb as part of non-project work
Notes: This is our new process, version 1.0
“Library Technology Council Proposal Submission, Review, and Approval Process”
Explain what LTC is
Goal: transparency, planning, not too slow
Premise: set aside some resources for “projects”. Proposed projects clearly state how many resources they need.
For all tech, not just dig coll
It’s formal.
Submit any time. For big initiatives, twice-yearly decisions.
Responsible, allows prioritization. But not nimble.
Don’t need to go into the details. But review some notable features:
(next slide)

## Slide 6
Receive proposal
Assign CDLA facilitator
Post proposal for CDLA/Systems/LTC review
Report to LTC
Develop full project proposal/timeline
Develop basic project plan/timeline
Project/workflow/time analysis
General estimate of required resources
Identify stakeholders
Preliminary decision on proposal disposition
Candidate for fast-track approval
Require full LTC review
Approve and proceed immediately
Report to LTC
LTC semiannual review
Compare required resources to available resources
Place in holding queue for priority if resource availability changes
Resources become available before next LTC review
Final decision on proposal disposition
Resources available
Resources not available
No
Yes
Require full LTC review
Fast-track approval
Estimate of required resources
Absorb as part of non-project work
“Facilitator” from the Carolina Digital Library and Archives
Notes: Facilitator’s role:
Assist communication between content and tech staff
Ask the right questions
Knowledge of technical aspects – what we’re already set up to do, what our next infrastructure priorities are, and what’s out there as a possibility
Help through logistics of process
Build skills in project planning among library staff
This is a new CDLA service

## Slide 7
Receive proposal
Assign CDLA facilitator
Post proposal for CDLA/Systems/LTC review
Report to LTC
Develop full project proposal/timeline
Develop basic project plan/timeline
Project/workflow/time analysis
General estimate of required resources
Identify stakeholders
Preliminary decision on proposal disposition
Candidate for fast-track approval
Require full LTC review
Approve and proceed immediately
Report to LTC
LTC semiannual review
Compare required resources to available resources
Place in holding queue for priority if resource availability changes
Resources become available before next LTC review
Final decision on proposal disposition
Resources available
Resources not available
No
Yes
Require full LTC review
Fast-track approval
Estimate of required resources
Absorb as part of non-project work
For some initiatives, allow “fast track” approval.
Notes: Administrators explicitly wanted a mechanism to compare possible initiatives against one another.
But can move more quickly in some cases.
Our criteria:
Something we already know how to do
Doesn’t take too many resources

## Slide 8
Receive proposal
Assign CDLA facilitator
Post proposal for CDLA/Systems/LTC review
Report to LTC
Develop full project proposal/timeline
Develop basic project plan/timeline
Project/workflow/time analysis
General estimate of required resources
Identify stakeholders
Preliminary decision on proposal disposition
Candidate for fast-track approval
Require full LTC review
Approve and proceed immediately
Report to LTC
LTC semiannual review
Compare required resources to available resources
Place in holding queue for priority if resource availability changes
Resources become available before next LTC review
Final decision on proposal disposition
Resources available
Resources not available
No
Yes
Require full LTC review
Fast-track approval
Estimate of required resources
Absorb as part of non-project work
Others get queued up for a big review every 6 months.
Notes: Submitting a proposal starts a planning phase
There’s a deadline after which proposals won’t be considered in this cycle. 2.5 months before decision date
We know this doesn’t meet every need, especially if grants are involved. Decided benefits outweighed drawbacks.

## Slide 9
Receive proposal
Assign CDLA facilitator
Post proposal for CDLA/Systems/LTC review
Report to LTC
Develop full project proposal/timeline
Develop basic project plan/timeline
Project/workflow/time analysis
General estimate of required resources
Identify stakeholders
Preliminary decision on proposal disposition
Candidate for fast-track approval
Require full LTC review
Approve and proceed immediately
Report to LTC
LTC semiannual review
Compare required resources to available resources
Place in holding queue for priority if resource availability changes
Resources become available before next LTC review
Final decision on proposal disposition
Resources available
Resources not available
No
Yes
Require full LTC review
Fast-track approval
Estimate of required resources
Absorb as part of non-project work
Develop a formal project plan.
Notes: Project plan templates have the usual features:
Justification
User impact
Assessment plan
Timeline/resources
Developed by a team, including both content and technical staff.
Forces planning. But is bureaucracy.
Goal is to use this as a valuable planning tool, not be seen as a barrier.
Resource estimates are fiction, but a necessary one.
Note traditional project management approach. More on this later.

## Slide 10: Resource allocation
Predetermine what’s available:
  Systems administration tasks
  Application development
  Visual design
  Scanner time
  Hourly students to digitize
  Metadata creation
  Storage
  etc
Different metrics for different categories
10% cap for fast-tracked approval

## Slide 11: What happened in this review cycle
20 proposals received (including legacy proposals)
  10 approved as fast-tracked
  8 approved as full review
  Nothing actually rejected
All new proposals submitted at once
Nearly all for relatively small things
2-month planning phase was extremely busy
Notes: We had the resources to approve everything! This was definitely a surprise.
Good outcome: data to reduce fear, uncertainty.
But should we have approved everything? What’s the role of resources vs. stated priorities?
Deadlines really influenced timing/pace of submission. This is definitely not what we want.
Just because it’s new and misunderstood? Or a fundamental part of human nature re: deadlines?
Fast track approvals weren’t fast enough. Just growing pains?

## Slide 12: assessment
In project plans
  Required section
  What we got was pretty basic
Of the process
  Survey of all library staff
  Focus group with CDLA facilitators
  Focus group with Systems staff
  Focus group with Library Technology Council members
  Individual interviews with proposers who volunteered
Notes:   New (30%) Assessment Coordinator
  Identified as a Library Technology Council priority for activities through end of 2012
In project plans
“we’ll look at google analytics” or somehow else count things
Didn’t go far enough in talking about impact
Of process
Report out next week
Expect changes as a result

## Slide 13: What we’ve learned (so far)
Administrators happy with the planning done; see progress; happy to issue approvals
Proposers view process as too burdensome
Current fast-track vs. full review setup has holes
Push more justification to the proposal stage
Planning phase isn’t enough for technical decisions in all cases
We need more assessment training
Resource estimation is even harder than we thought
Facilitating proposals is a lot of work!

## Slide 14: What about agility?
Photo by radloff. http://www.flickr.com/photos/radloff/6708510227/
Notes: Those of you who know the literature on agile software development and agile project management will likely have seen in this process many of the weaknesses of traditional project management approaches that agile approaches provide an alternative to. We realize this,
Our process focuses on planning. Planning is good and not incompatible with agile.
Some challenges:
Need agility across projects, not just within an individual one
We’re not just planning software development projects
We’re not (currently) an agile organization. We probably never will be.
But there are some opportunities:
This could be a way to take some steps towards agile. There’s value in that.
Get proposers and tech staff more invested in the work
Clear need for iteration in our process

## Slide 15: Next steps towards sustainability
Photo by Trevor Haldenby. http://www.flickr.com/photos/trevorh/491898939/
Notes: While maintaining growth and innovation
Sunsetting projects
Sunsetting technologies
Clear expectations – boundaries without negativity
Re-evaluate tech/initiatives we support after a time, without too much work or oversight
Cuture of experimentation – give room, don’t assume next step is a certainty
Promote the wide view
Iterate our outlook, plans, and processes

## Slide 16: Thank you!
jennriley@unc.edu
These slides: http://www.lib.unc.edu/users/jlriley/presentations/ltcProcess/duke2012.pptx